## Test Cases
Test Case ID | Date | Tester's Name | Test Scenario | Description | Pre-Condition | Test Steps | Expected Result | Actual Result | Status
TC_01 | 2026-02-10 | Utkarsh | Home Page | Verify home page loads | Internet available | Open website URL | Home page should load | Home page is loading | pass
TC_02 | 2026-02-10 | Utkarsh | Registration | Verify user registration with valid data | User not registered | Click Register, fill form, submit | User should register successfully | Resgistered successfully | pass
TC_03 | 2026-02-10 | Utkarsh | Registration | Verify registration with existing email | User already registered | Register with same email | Error message should display | Error Displaying | pass
TC_04 | 2026-02-10 | Utkarsh | Login | Verify login with valid credentials | User registered | Enter valid email & password | User should login | Login in | pass
TC_05 | 2026-02-10 | Utkarsh | Login | Verify login with invalid credentials | User registered | Enter wrong password | Error message should display | Error Displaying | pass
TC_06 | 2026-02-10 | Utkarsh | Search | Verify product search | Website open | Enter product name in search box | Product results should display | Result displaying | pass
TC_07 | 2026-02-10 | Utkarsh | Category | Verify category navigation | Website open | Click Electronics category | Category page should open | opens | pass
TC_08 | 2026-02-10 | Utkarsh | Product Page | Verify product details page | Website open | Click on product | Product details should show | details are shown | pass
TC_09 | 2026-02-10 | Utkarsh | Add to Cart | Verify add product to cart | Product page open | Click Add to Cart | Product should be added to cart | product added to cart | pass
TC_10 | 2026-02-10 | Utkarsh | Cart | Verify cart page loads | Cart has items | Click Shopping Cart | Cart page should display | Cart page displayed | pass
TC_11 | 2026-02-10 | Utkarsh | Update Cart | Verify quantity update in cart | Item in cart | Change quantity and update | Quantity should update | Quantity updated successfully | pass
TC_12 | 2026-02-10 | Utkarsh | Remove Cart | Verify remove product from cart | Item in cart | Click Remove button | Product should be removed | Product removed | pass
TC_13 | 2026-02-10 | Utkarsh | Checkout | Verify checkout process | User logged in, item in cart | Click Checkout | Checkout page should open | Checkout page opened | pass
TC_14 | 2026-02-10 | Utkarsh | Payment | Verify payment method selection | Checkout page open | Select payment method | Payment method should select | Payment method selected | pass
TC_15 | 2026-02-10 | Utkarsh | Order | Verify order confirmation | Payment done | Place order | Order confirmation should show | Order confirmation displayed | pass
TC_16 | 2026-02-10 | Utkarsh | Logout | Verify logout functionality | User logged in | Click Logout | User should logout | User logged out | pass
TC_17 | 2026-02-10 | Utkarsh | Footer Links | Verify footer links | Website open | Click footer links | Correct pages should open | All pages opened correctly | pass
TC_18 | 2026-02-10 | Utkarsh | UI | Verify UI alignment | Website open | Check layout and alignment | UI should be proper | UI displayed properly | pass
TC_19 | 2026-02-10 | Utkarsh | Performance | Verify page load time | Internet available | Open website | Page should load within min 5 sec | Page loaded within acceptable time | pass
TC_20 | 2026-02-10 | Utkarsh | Security | Verify password masking | Login page open | Enter password | Password should be masked | Password masked properly | pass

## Bugs Report
Bug ID | Bug Title | Module | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG_01 | Login button UI misaligned | Login Page | 1. Open login page | Login button should be properly aligned | Login button is slightly misaligned | Low | Low | Open
2. Observe login button
BUG_02 | Registration allows weak password | Registration | 1. Go to Register | System should show password strength error | User can register with weak password | Medium | Medium | Open
2. Enter weak password
3. Submit
BUG_03 | Search returns no result for valid product | Search | 1. Enter 'Laptop' in search | Relevant products should display | No products displayed sometimes | High | High | Open
2. Click search
BUG_04 | Add to cart button not responsive | Product Page | 1. Open product page | Product should be added to cart | Button does not respond on first click | High | High | Open
2. Click Add to Cart
BUG_05 | Cart quantity not updating | Cart | 1. Add item to cart | Quantity should update to 2 | Quantity remains 1 | Medium | High | Open
2. Change quantity to 2
3. Update
BUG_06 | Checkout page slow loading | Checkout | 1. Add item to cart | Checkout page should load within 3 sec | Checkout page loads after 10+ seconds | Medium | Medium | Open
2. Click Checkout
BUG_07 | Logout button not visible on mobile | Responsive UI | 1. Open site on mobile view | Logout option should be visible | Logout button is hidden | Low | Low | Open
2. Check logout option
BUG_08 | Footer link opens wrong page | Footer | 1. Scroll to footer | About Us page should open | Contact page opens instead | Low | Low | Open
2. Click About Us link
BUG_09 | Password field not masked on register | Registration | 1. Go to Register | Password should be hidden with dots | Password is visible in plain text | High | High | Open
2. Enter password
BUG_10 | Order confirmation message not displayed | Order | 1. Complete checkout | Order confirmation message should display | Blank page shown | Critical | High | Open
2. Place order